## Inspection RWHS (Malls)
S. No. | Ref. No. | Team No | District | Name & Address of Mall/ Commercial Project | Inspected by (Committee No.) | Date of Inspection | Status of RWHS as per Inspection | Remarks/ Suggestions | Remarks | Reply recd on
1 | 3 | Team 5 | South | M/s Aditya Infracon Pvt. Ltd., Plot No :08, Jasola District Centre, New Delhi. | V | 17.04.2015 | Satisfactory | Regular maintenance of the structure is required . No DJB water connection , one STP exist. Water supply through tankers. |  | 24.11.2014
2 | 15 | 1 | South | M/s DLF Universal Ltd. DLF Courtyard" Plot Nos. A-4 and P-1A at Saket Place, Saket, New Delhi. | I | 06.02.2015 | Satisfactory | Functional. Modify according to be design of CGWB. |  | Prior to 30.10.2014
3 | 17 | Team 5 | South | M/s DLF Ltd. Plot No. 79-80 Okhla Phase-I, New Delhi. | V | 15.04.2015 | Satisfactory | Three RWH exist. Design not approved by Govt. Agency. In Structure micron filter exist & mis filter exis all the structures. Borewell not visible structured covered by pathway. No DJB connection, no gw boring, water supply through water supplier. STP exist yet to start due to non- occupancy of the building. |  | Prior to 30.10.2014
4 | 35 | 1 | South West | M/s Oak Infrastructure Developer Limited, Asset No.-08, Hospitality District, DIAL, Indira Gandhi International Airport, Delhi. | I | 03.02.2015 | Satisfactory | Water found in pit 2 near out gate. Water should not be stagnant beyond retentional period. |  | 21.11.2014
5 | 38 | Team 3 | West | M/s P.P.Buildwell Pvt. Ltd., West End Mall Plot no. 15-16, Tower block site, District Centre, Janakpuri, New Delhi. | III | 10.04.2015 | Satisfactory | No Remarks |  | 03.11.2014
6 | 45 | 3 | West | M/s Shoppers Stop Ltd. No.10, Shivaji Place, District Centre, Raja Garden,New Delhi. | III | 09.02.2015 | Satisfactory | No Remarks |  | 13.11.2014
7 | 46 | Team 6 | North | M/s SMS Infrastucture Limited, Automated Multilevel Car Parking cum Commercial Complex, Kamla Nagar, Delhi | VI | 31.03.2015 | Satisfactory | Only rain water from the roof top of the premisies is to be harvested, all the drains are to be cleaned regularly, wire mesh may be fitted in the inlet of RWH pit & periodic/annual maintenance of the RWH system and borewell is to be done regularly. |  | 03.11.2014
8 | 48 | Team 4 | East | M/s STC Developers (P) Ltd., Cross River Mall, Plot No 9B, 9C, Central Buisness, District Shahdara. | IV | 20.04.2015 | Satisfactory | No Remarks |  | 14.11.2014
9 | 53 | Team 4 | East | M/s YMC Builders Pvt. Ltd, V3S East Centre at Plot N. 12, Laxmi Nagar District Centre, Vikas Marg, New Delhi. | IV | 20.04.2015 | Satisfactory | No Remarks |  | Prior to 30.10.2014
10 | 1 | 1 | South | M/s ABW Infrastructure Ltd. Rectangle-1, D-4, Saket District Centre, New Delhi-110017. | I | 06.02.2015 | Not Satisfactory | No approved design -Not sufficient as all the roof top rain water is not being collected. |  | 24.11.2014
11 | 2 | Team 5 | South | M/s Aditya Infra Developers Pvt. Ltd., Plot: - No-5, Jasola District Centre, New Delhi. | V | 08.04.2015 | Not Satisfactory | Water is stagnant in both structures. Recharge well checked . Filter media should be replaced with immediate effect. No gw boring , no DJB water Supply. One STP exists. Water Supplied by pvt. Tankers. |  | 10.11.2014
12 | 4 | Team 4 | East | M/s Aggarwal Plaza Pvt. Ltd., AGGARWAL METRO PLAZA, Plot No. 29 and 31, CBD Shahdara, Commercial complex, Delhi. | IV | 20.04.2015 | Not Satisfactory | RWH system needs redevelopment wrt filter media. |  | 30.10.2014
13 | 7 | Team 3 | West | M/s Anant Raj Projects Ltd. 67 Najafgarh Road, Kirti Nagar, New Delhi. | III | 23.03.2015 | Not Satisfactory | (1) Stagnent water absorve 2.5 mt in all pits. (2) Filter media required cleaning & RWH to be made functional.(3) Surface drain are found canceled & required to be disconnected. | Notice returned back undilivered. | 17.11.2014
14 | 10 | Team 5 | South | M/s Brightways Housing and Land Development Pvt Ltd., Plot No.7, Non Hierarchical Commercial Centre, Jasola, Delhi. | V | 08.04.2015 | Not Satisfactory | In one structure water is stagnant. It seems that filter media not cleaned reqularly. Filter media should be replaced with immediate effect. One gw boreing, one STP exists. No DJB connection exist. |  | Prior to 30.10.2014
15 | 12 | 1 | South West | M/s Divine Infracon Pvt. Ltd. Hotel complex at Plot no. 4, Sector-13, Dwarka, New Delhi | I | 03.02.2015 | Not Satisfactory | Filled with water not funcional . Needs immidiate repair. |  | 14.11.2014
16 | 14 | Team 4 | East | M/s DLF Ltd. DLF - The Galleria Shopping Mall" Plot No.113, District Centre, Mayur Place, Mayur Vihar Phase-I, Delhi. | VIII | 25.03.2015 | Not Satisfactory | One pit is front side of Mall (metroline side) and second pit is back side of Mall (towards Eros Hotel) |  | Prior to 30.10.2014
17 | 18 | Team 5 | South | M/s DLF Home Developers Ltd. Plot nos.10, Jasola, New Delhi. | V | 15.04.2015 | Not Satisfactory | RWH is not constructed as per design. Not sufficient for two towers. Maintenance is under process. No gw boring, DJB connection exist but not supplying water. Water supply through private water tankers. one STP Exist. |  | Prior to 30.10.2014
18 | 19 | Team 5 | South | M/s DLF Home Developers Ltd. Plot nos.11, Jasola, New Delhi. | V | 15.04.2015 | Not Satisfactory | RWH is not constructed as per design. Not sufficient for two towers. Maintenance is under process. No gw boring, DJB connection exist but not supplying water. Water supply through private water tankers. one STP Exist. |  | Prior to 30.10.2014
19 | 21 | 1 | West | M/s DLF Retail Developers Ltd., DLF Towers” Plot Nos. 1 & 2, Najafgarh Road, Shivaji Marg, New Delhi. | I | 13.02.2015 | Not Satisfactory | Design of RWH system improper & surface drainage and Greace Trap as per drawing found connected with RWH Structure & directed to disconnect the immediately .- Stagnant water seen in the filtration chambers . |  | Prior to 30.10.2014
20 | 22 | 3 | West | M/s GPS Properties Pvt. Ltd. West Gate Mall, Plot No.4,5,6 , District Centre, Raja Garden,New Delhi. | III | 09.02.2015 | Not Satisfactory | Swage seen in the recharge pit in the second RWH system . As reported, it is due to the damage by DMRC work near the mall. No visible cracks observed. |  | Prior to 30.10.2014
21 | 23 | Team 5 | South | M/s GYS Real Estate Pvt Ltd., D-3 & P-3B District Centre, Saket, New Delhi. | V | 15.04.2015 | Not Satisfactory | RWH structure is coverd is covered /Not visible/ IT seems that RWH does not exist. No DJB water supply, No Gw Boring. STP exist. Water Supply through private tankers. |  | Prior to 30.10.2014
22 | 27 | 1 | South West | M/s Jasmine projects private Ltd., (Bharti Reality Ltd.) Plot no. 1, vasant kunj shopping mall site, vasant kunj, new delhi | I | 12.02.2015 | Not Satisfactory | Water logged. Water stagnant indicating no function . Requirs immidiate cleaning.Details of the structure and cancernd person were not available. |  | 03.11.2014
23 | 28 | Team 5 | South | M/s Laxmi Buildtech Pvt. Ltd. Ras Vilas, Plot no. D 1, and P3A. Saket Place, New Delhi. | V | 15.04.2015 | Not satisfactory | Structures are filled up with silt material. In one structure waste material also seen. Replacement of filter media/cleaning of the structure is necessary with immediate effect. No gw boring, no. DJB connection, waer supply through private tankers, STP exist. |  | 24.11.2014
24 | 32 | 1 | South | M/s MGF Developments Limited Metropolitan Mall, District Centre Saket, Delhi. | I | 06.02.2015 | Not satisfactory | Not Functional. RO Water should not be allowed in the pits. Immidiate Cleaning is required. |  | Prior to 30.10.2014
25 | 33 | Team 3 | West | M/s Naman Builders Ltd Pacific Mall Commercial Complex, Khyala, New Delhi. | III | 06.04.2015 | Not satisfactory | 1. Stagnent water seen in the RWH chamber. (2) Drg of RWH not available as well as pit cannot be acessable to take diversions & diversion above are as informed by the representative of mall.(3) Surface drainage also found canceled with RWH |  | Prior to 30.10.2014
26 | 50 | 1 | South West | M/s Tirupati Buildings and offices (P) Ltd., Hotel complex at plot no. 3, Sector-10, Dwarka, new delhi | I | 03.02.2015 | Not Satisfactory | Not Functional. Water logged found in all 3 pits indicating not functional. Requires immidiate cleaning. Remarks of unit :- The rain water wells are as per design, the next due maintaince is being prepared and any discribancy will be sort out and rectified for inspection in next 20 days from today. |  | 30.10.2014
27 | 5 | 1 | South West | M/s Ambience Developers Pvt. Ltd., Ambience Mall, plot no. 2, Vasant Kunj Mall, Vasant Kunj, New Delhi. | I | 12.02.2015 | _____ | Functional .Requires periodic cleaning. |  | Prior to 30.10.2014
28 | 8 | 1 | South West | M/s Aspen Buildtech Limited, sset No.-11, Hospitality District, DIAL, IGI Airport, Delhi. | I | 03.02.2015 | _____ | No Remarks. Team striked their remarks. |  | 21.11.2014
29 | 9 | 1 | South West | M/s Beverly Park Maintance Services Ltd Beverly Park, Plot No.3, Vasant Kunj, Nelson Mandela Road, New Delhi. | I | 12.02.2015 | _____ | Pit No. 4, Infrant of promonade requires to be cleaned immidietily. | Notice returned back undilivered. | 28.10.2014
30 | 34 | 1 | South West | M/s Oak Infrastructure Developer Limited, Asset No.-07, Hospitality District, DIAL, Indira Gandhi International Airport, Delhi. | I | 03.02.2015 | _____ | No Remarks |  | 21.11.2014
31 | 42 | 1 | South West | M/s Regency Park Property Management Services Ltd., Plot No.4, Vasant Kunj, Nelson Mandela Road, New Delhi. | I | 12.02.2015 | _____ | No Remarks | Notice returned back undilivered. | 28.10.2014
32 | 44 | 1 | South | M/s Select Infrastructure Pvt. Ltd. Select City Mall District Centre, Saket, New Delhi. | I | 06.02.2015 | _____ | Working condition. Record of periodic cleaning should be maintain. Should report to CGWA/DJB with date. |  | 30.10.2014
33 | 58 | Team 3 | West | M/s Gold Cause Construction Pvt. Ltd. Paradise Mall, Plot No. 23, Shivaji Place, District Centre, Raja Garden, New Delhi. | III | 23.03.2015 | _____ | Couldnot be inspected as RWH structures covered with earth as the Mall under caust. Advice to demane the earth to makeit acess for inspection & inform. |  | Prior to 30.10.2014
34 | 60 | Team 6 | North | M/s MGF Developments Ltd, MGF City Mall at Khyber Pass, MGF House, 17-B, Asaf Ali Road, New Delhi. | VI | 26.03.2015 | _____ | Construction of building not started. | Project under construction. | 12.11.2014
35 | 6 | Team 6 | North West | M/s Ambience Towers Pvt. Ltd., Shopping cum Commercial Complex”, Plot No-2B2, Twin District Centre, Sector-10, Rohini, New Delhi | II | 05.02.2015 | Satisfactory | Proper maintenance of conveyance system and filter media is to be done before onset of monsoon. |  | Prior to 30.10.2014
36 | 20 | Team 6 | North West | M/s DLF Ltd., DT CITY CENTER, Community City Center Site Block-A, Shalimar Bagh, New Delhi-88. | II | 12.03.2015 | Not Satisfactory | Make the RWH system functional & annual/Periodic maintenance of the filter medium and development of bore hole is to carried out regularly. |  | Prior to 30.10.2014
37 | 24 | Team 6 | North West | M/s Jakson Developers Pvt. Ltd., City Centre Mall Plot no. 1B3, Twin District Center, Sector-10, Rohini, Delhi. Office address : 2nd Floor, Hotel Crowne Plaza, Plot no. 3B1, Twin District Center, Sector-10, Rohini, Delhi. | II | 04.02.2015 | Satisfactory | keep the system leak proof and neat and clean with periodic checking and maintenance. | As water table is high, collection tank and reuse system provided. | Prior to 30.10.2014
38 | 25 | Team 6 | North West | M/s Jakson Developers Pvt. Ltd., Hotel cum Commercial Complex Plot No. 3B1, Twin distt. Center, Sector-10, Rohni,Delhi. Office address : 2nd Floor, Hotel Crowne Plaza, Plot no. 3B1, Twin District Center, Sector-10, Rohini, Delhi. | II | 04.02.2015 | Satisfactory | keep the system leak proof and neat and clean with periodic checking and maintenance. | As water table is high, collection tank and reuse system provided. | Prior to 30.10.2014
39 | 26 | Team 6 | North West | M/s Jakson Buildwell Pvt. Ltd., V3S Ring Road Mall, Plot no. 21, Sec-3, Manglam Place, Delhi. Office Address: 5th Floor, Block-A, NDM-1, Plot No. B-2,3,4, Nataji Subhash Place, Delhi-34. | II | 04.02.2015 | Satisfactory | keep the system leak proof and neat and clean and maintain properly through periodic checkup of the system. | As water table is high, collection tank and reuse system provided. | Prior to 30.10.2014
40 | 29 | Team 1 | South | M/s Lifestyle Builders Pvt Ltd SALCON AURUM, Plot no.11, Jasola, New Delhi. | V | 20.04.2015 | Not Satisfactory | The pit size and number of pits to be rechocked for adequate size, Pipe above filter bed should be blinde. |  | 24.11.2014
41 | 30 | Team 6 | North West | M/s Mera Baba Reality, Associates Pvt. Ltd. “D” Mall, Plot No. A-1, District Centre, Wazirpur (Netaji Subhash Place), New Delhi | II | 06.02.2015 | Satisfactory | Desilting pit should be keep clean. Waste water should not enter this pit & Annual maintenance before onset of monsson is to carried out regularly/every year. |  | 19.11.2014
42 | 31 | Team 6 | North West | M/s Mera Baba Reality, Associates Pvt. Ltd., D MALL, Rohini, Plot No-1B5, Twin District Centre, Rohini, Delhi | II | 05.02.2015 | Satisfactory | filter media in both the Rain Water Harvesting structures is to cleaned and refilled with proper filter medium i.e. Gravel & Coarse sand etc., Annual maintenance before onset of monsoon ir to be carried out & the bore in the RWHS opp. McDonald is to be re developed with compressor so that the structure becomes more effective. |  | 19.11.2014
43 | 36 | Team 6 | North West | M/s Omaxe Construction Ltd. "Pearl Omaxe" Netaji Subhash Place, Wazirpur, New Delhi-34. | II | 11.02.2015 | Satisfactory | Any type of water other than rainwater should not be allowed to enter the rain water harvesting structure, Coarse sand is to be refilled in both the RWH Structures & Annual/Periodic maintenance of both the RWH structures is to be done regularly before onset of monsoon. |  | 24.11.2014
44 | 37 | Team 2 | North West | M/s P P Buildwell Pvt. Ltd., PP Trade Centre- Commercial cum Multilevel Parking Complex, Plot No.1, Netaji Subhash Place, Delhi. | II | 06.02.2015 | Satisfactory | Annual maintenance/ Periodic maintenance of Rain water harvesting system is to be carried out regularly & Only rain water is to be recharged through these structures. |  | 03.11.2014
45 | 41 | Team 2 | North West | M/s Pragya Products(P) Limited, "Shop- In- Park- North" Commercial Complex at Plot No. 2, Block-B Community Centre, Shalimar Bagh, New Delhi. | II | 11.03.2015 | Partially Satisfactory | Structure number 2 and 3 are to be cleaned and bore to be redeveloped, all the drains are to be clean & annual/periodic maintenance is to be done regularly. |  | 30.10.2014
46 | 47 | Team 1 | South | M/s Splendor Landbase Ltd, Splendor Forum, Plot no.11, Jasola, New Delhi | V | 20.04.2015 | _____ | Pit No 2 is checked, one pit near to out gate is not functional it needs to be cleaned and filter bed changed. |  | Prior to 30.10.2014
47 | 49 | Team 1 | South West | M/s Suncity Project Pvt. Ltd. Vasant Square Mall Plot No-A, Pocket-V, Sector-B, Vasant Kunj,New Delhi. | V | 25.02.2015 | Not Satisfactory | Not clean, Deign should be rechecked for adequacy. |  | Prior to 30.10.2014
48 | 51 | Team 2 | North West | M/s Unitech Amusement Parks Ltd., Amusement Park, Sector 10, Rohini, Delhi-85 | II | 11.03.2015 | Satisfactory | Annual/Periodic maintenance of all the structures is to done regularly & any water other than rain water should not be allowed to enter the rain water harvesting structures. |  | Prior to 30.10.2014
49 | 52 | Team 2 | North West | M/s Upaj Buildcon Pvt. Ltd, Kings Mall Parking cum commercial complex at Plot no. 1831, Twin District Centre Sector-10 Rohini, New Delhi. | II | 04.02.2015 | Not Satisfactory | Filter media is to be cleaned, proper filter media i.e. Gravel and coarse and is to be filled in both the Rain Water Harvesting Structures, Conveyence systrem is to be redeveloped so that rain water reaches the pit & Periodic maintenance of the system has to be carried out. |  | 27.11.2014
50 | 55 | Team 2 | North West | M/s Ambience Towers Pvt. Ltd., Shopping cum Commercial Complex”, Plot No.10, Community Centre, Block B, Shalimar Bagh, New Delhi. | II | 12.03.2015 | Partially Satisfactory | Pit no. 2 is to be clean, filter medium is to washed and borewell to be redevelped so that the RWH structure becomes functional & periodiec/annual maintenance of both the structures is to be carried out regularly, only rain water is to be harvested through RWH structure & all the drain are to be kept clean. |  | Prior to 30.10.2014
51 | 56 | Team 2 | North West | M/s Best International Projects Pvt. Ltd.Delhi. Multilevel Car Parking cum Commercial Complex, Netaji Subhash Place, Wazirpur, Delhi. Office Address: 1st floor, Best Plaza, Plot No, H-8, Netaji Subhash Place, Wazirpur, New Delhi. | II | 06.02.2015 | _____ | No Remarks | Project under construction. | Prior to 30.10.2014
52 | 61 | Team 2 | North West | M/s Parsvnath Developers Ltd. , Office cum Commercial tower , Netaji Subhash Place Metro Station Opposite Wazirpur District Centre, Pitampura,Delhi. Office Address: Parsvnath Metro Tower, Near Shahdara Metro Station, Shahdara, Delhi-32. | II | 06.02.2015 | _____ | No Remarks | Project not started so far. | Prior to 30.10.2014
53 | 62 | Team 2 | North West | M/s Parsvnath Developers Ltd. Parsvnath Mall Commercial Complex Project, Plot No. 1 B2, Twin District Centre, Sector-10, Rohini, New Delhi. Office Address: Parsvnath Metro Tower, Near Shahdara Metro Station, Shahdara, Delhi-32. | II | 05.02.2015 | _____ | Under Construction. | Project under construction. | Prior to 30.10.2014